## Risk Register
Risk ID | Risk Description | NIST RMF Function | Likelihood (1-5) | Impact (1-5) | Risk Score | Risk Rating | Current Controls | Planned Mitigation (POA&M) | Owner | Due Date | Status | Date Identified | Last Updated
RISK-001 | Detection accuracy not validated across site lighting, PPE variation, or worker demographics | Measure | 4 | 5 | 20 | High | Vendor benchmark data only; no site-specific testing | Commission independent accuracy & fairness validation study covering lighting, PPE, and demographic variation | AI Governance Lead | 2026-11-15 | Open | Open | Open
RISK-002 | No named accountable owner for the safety camera AI system | Govern | 3 | 4 | 12 | Medium | Informal split between EHS and IT | Formally name EHS Safety Director as accountable owner; document in AI System Register | EHS Safety Director | 2026-09-05 | Open | Open | Open
RISK-003 | No AI-specific acceptable use policy in force | Govern | 3 | 4 | 12 | Medium | General IT acceptable use policy exists but doesn't cover AI-specific risk | Adopt drafted Acceptable Use Policy; route through Legal and EHS sign-off | AI Governance Lead | 2026-09-05 | Open | Open | Open
RISK-004 | No defined incident protocol when AI fails to catch a real hazard | Manage | 3 | 5 | 15 | High | Standard EHS incident investigation process exists but lacks an AI-specific root-cause category | Add 'AI system contribution' category to incident investigation template; define escalation path | EHS Safety Director | 2026-10-01 | Open | Open | Open
RISK-005 | No documented consequence analysis for false positives vs. false negatives | Map | 2 | 3 | 6 | Low | Anecdotal awareness among supervisors only | Conduct formal impact analysis weighting false negatives (missed hazards) above false positives | AI Governance Lead | 2026-10-15 | Open | Open | Open
RISK-006 | No pre-defined criteria or authority to roll back / pause the system if found unsafe | Manage | 2 | 4 | 8 | Medium | Technically possible via IT; no documented trigger or decision authority | Document rollback criteria and named joint EHS/AI Governance decision authority | IT Security | 2026-10-15 | Open | Open | Open
RISK-007 | Workers not formally notified of AI monitoring at all site zones | Govern | 2 | 3 | 6 | Low | Partial signage in some zones; no onboarding disclosure | Roll out standardized signage and add disclosure to new-hire onboarding | Site Supervisor | 2026-09-20 | Open | Open | Open
RISK-008 | No ongoing performance monitoring dashboard post-deployment | Measure | 2 | 3 | 6 | Low | Vendor provides periodic model updates only; no internal tracking | Stand up quarterly performance review using logged alerts vs. confirmed incidents | AI Governance Lead | 2026-12-01 | Open | Open | Open

## Legend & Instructions
How to use this register
Each row is a discrete AI governance risk. Risk Score = Likelihood x Impact (auto-calculated). Risk Rating is auto-derived: High >= 15, Medium 8-14, Low <= 7.
Scoring guide (Likelihood and Impact, 1-5 each):
1 = Rare / Negligible 3 = Possible / Moderate 5 = Almost Certain / Severe (safety incident or regulatory action)
Update cadence: Owners should update Status and Last Updated at minimum monthly for High risks, quarterly for Medium/Low.
Yellow-filled cells (Status, Due Date, Last Updated) are the fields owners are expected to actively maintain.
This register is the operational companion to the NIST AI RMF Gap Assessment — each risk traces back to a specific finding there.

## Portfolio Metadata
AI Governance Portfolio
Portfolio Owner | David Amoako-Attah
Role | AI Governance Analyst
Portfolio Date | 2026-08-08
Scenario Start Date | 2026-08-08
Target Initial Governance Review | 2026-08-15
Note | Operational business/accountable owners are preserved; this sheet identifies the portfolio author and scenario timeline.
Suggested POA&M Milestone | Target Date
Assign accountable system owner / approve AUP | 2026-08-15
Complete site-specific validation study | 2026-09-18
Establish quarterly performance review | 2026-11-06